## OPEN Cases for TAC
HC Date | HC Id | Node IP | Location | Node User Label | NE Type | Network | Test Case | Category | Issue | Finding | Task | Status | Int/Ext | Flt Categ | HW Type | Card Sl# | Remarks
2024-02-05 | 102034 | 10.151.20.16 | OUE | OUE-R-1 | 1830PSS32-WDM | OPT_NC | 0.6 | WARNING | System Identity | wrong SID found: found CSM-R-1 vs userlabel OUE-R-1 | Verify correct Identity and fix SID or <customer>_hosts.xls. | OPEN | Int | TBD
2024-11-19 | 172281 | 10.151.20.20 | POI | POI-R-1 | 1830PSS32-WDM | OPT_NC | 5.5.0 | WARNING | Read Remote Inventory | some UNKNOWN interface 3/11/C1 (PN: RA01, SN: NOK) found | not applicable | OPEN | Int | TBD
2024-11-19 | 172281 | 10.151.20.20 | POI | POI-R-1 | 1830PSS32-WDM | OPT_NC | 5.5.0 | WARNING | Read Remote Inventory | some UNKNOWN interface 3/11/C2 (PN: RA01, SN: NOK) found | not applicable | OPEN | Int | TBD
2025-01-17 | 106267 | 10.151.20.10 | HOU | HOU-R-1 | 1830PSS32-WDM | OPT_NC | 5.5.0 | WARNING | Read Remote Inventory | some UNKNOWN interface 2/17/X6 (PN: 1AB390930014, SN: ALLU17--CNDG520005) found | not applicable | OPEN | Int | TBD
2025-02-27 | 189695 | 10.151.11.21 | NOU | NOU-1 | 1830PSS32-WDM | OPT_NC | 5.2.4 | WARNING | Check SNMP trap destination | No appropriate SNMP trap destination found | Check SNMP connection between NE and Target Address | OPEN | Int | TBD
2025-03-03 | 106267 | 10.151.20.10 | HOU | HOU-R-1 | 1830PSS32-WDM | OPT_NC | 5.5.0 | WARNING | Read Remote Inventory | some UNKNOWN interface 2/17/X5 (PN: 1AB390930014, SN: ALLU17--CNDG520006) found | not applicable | OPEN | Int | TBD
2025-03-03 | 122344 | 10.151.12.21 | GAL | GAL-1 | 1830PSS32-WDM | OPT_NC | 5.5.1 | WARNING | Check cards in proper operational state | card 3/16 (11DPM12) operational Down | confirm the operational state of cards together with customer | OPEN | Int | TBD
2025-03-03 | 164831 | 10.151.20.21 | PK5 | PK5-R-1 | 1830PSS32-WDM | OPT_NC | 5.5.1 | WARNING | Check cards in proper operational state | card 2/12 (11DPM12) operational Down | confirm the operational state of cards together with customer | OPEN | Int | TBD
2025-03-03 | 164831 | 10.151.20.21 | PK5 | PK5-R-1 | 1830PSS32-WDM | OPT_NC | 5.5.1 | WARNING | Check cards in proper operational state | card 3/14 (11OPE8) operational Down | confirm the operational state of cards together with customer | OPEN | Int | TBD
2025-03-03 | 164831 | 10.151.20.21 | PK5 | PK5-R-1 | 1830PSS32-WDM | OPT_NC | 5.5.1 | WARNING | Check cards in proper operational state | card 3/15 (11OPE8) operational Down | confirm the operational state of cards together with customer | OPEN | Int | TBD
2025-03-03 | 180355 | 10.151.16.21 | DUC | DUC-1 | 1830PSS32-WDM | OPT_NC | 5.5.1 | WARNING | Check cards in proper operational state | card 2/13 (11OPE8) operational Down | confirm the operational state of cards together with customer | OPEN | Int | TBD
2025-04-04 | 111687 | 10.151.15.21 | PK5 | PK5-1 | 1830PSS32-WDM | OPT_NC | 5.6.9 | FAILURE | Check ONET Amps FW | AHPLG-1-1-15-0, PN (8DG59945AAAB01), SN (EZ1212A0168) needs to be upgraded to FW 1.1.4 | ONET FW 1.1.1 detected and needs to be updated to 1.1.4 | OPEN | Int | TBD
2025-04-04 | 111687 | 10.151.15.21 | PK5 | PK5-1 | 1830PSS32-WDM | OPT_NC | 5.6.9 | FAILURE | Check ONET Amps FW | AHPLG-1-1-3-0, PN (8DG59945AAAB01), SN (EZ1221A0069) needs to be upgraded to FW 1.1.4 | ONET FW 1.1.1 detected and needs to be updated to 1.1.4 | OPEN | Int | TBD
2025-04-04 | 119674 | 10.151.13.21 | VEL | VEL-1 | 1830PSS32-WDM | OPT_NC | 5.6.9 | FAILURE | Check ONET Amps FW | AHPLG-1-1-11-0, PN (8DG59945AAAB01), SN (EZ1216A0310) needs to be upgraded to FW 1.1.4 | ONET FW 1.1.1 detected and needs to be updated to 1.1.4 | OPEN | Int | TBD
2025-04-04 | 122344 | 10.151.12.21 | GAL | GAL-1 | 1830PSS32-WDM | OPT_NC | 5.6.9 | FAILURE | Check ONET Amps FW | AHPLG-1-1-15-0, PN (8DG59945AAAB01), SN (EZ1212A0047) needs to be upgraded to FW 1.1.4 | ONET FW 1.1.1 detected and needs to be updated to 1.1.4 | OPEN | Int | TBD
2025-04-04 | 122344 | 10.151.12.21 | GAL | GAL-1 | 1830PSS32-WDM | OPT_NC | 5.6.9 | FAILURE | Check ONET Amps FW | AHPLG-1-1-7-0, PN (8DG59945AAAB01), SN (EZ1220A1833) needs to be upgraded to FW 1.1.4 | ONET FW 1.1.1 detected and needs to be updated to 1.1.4 | OPEN | Int | TBD
2025-04-04 | 122344 | 10.151.12.21 | GAL | GAL-1 | 1830PSS32-WDM | OPT_NC | 5.6.9 | FAILURE | Check ONET Amps FW | AHPLG-1-1-10-0, PN (8DG59945AAAB01), SN (EZ113820179) needs to be upgraded to FW 1.1.4 | ONET FW 1.1.1 detected and needs to be updated to 1.1.4 | OPEN | Int | TBD
2025-04-04 | 130549 | 10.151.17.21 | TON | TON-1 | 1830PSS32-WDM | OPT_NC | 5.6.9 | FAILURE | Check ONET Amps FW | AHPHG-1-1-7-0, PN (8DG59245AAAB02), SN (EZ1324A2028) needs to be upgraded to FW 1.1.4 | ONET FW 1.1.1 detected and needs to be updated to 1.1.4 | OPEN | Int | TBD
2025-04-04 | 140398 | 10.151.14.21 | MAG | MAG-1 | 1830PSS32-WDM | OPT_NC | 5.6.9 | FAILURE | Check ONET Amps FW | AHPLG-1-1-6-0, PN (8DG59945AAAB01), SN (EZ120520162) needs to be upgraded to FW 1.1.4 | ONET FW 1.1.1 detected and needs to be updated to 1.1.4 | OPEN | Int | TBD
2025-04-04 | 140398 | 10.151.14.21 | MAG | MAG-1 | 1830PSS32-WDM | OPT_NC | 5.6.9 | FAILURE | Check ONET Amps FW | AHPLG-1-1-3-0, PN (8DG59945AAAB01), SN (EZ120420208) needs to be upgraded to FW 1.1.4 | ONET FW 1.1.1 detected and needs to be updated to 1.1.4 | OPEN | Int | TBD
2025-04-04 | 180355 | 10.151.16.21 | DUC | DUC-1 | 1830PSS32-WDM | OPT_NC | 5.6.9 | FAILURE | Check ONET Amps FW | AHPLG-1-1-7-0, PN (8DG59945AAAB01), SN (EZ120420051) needs to be upgraded to FW 1.1.4 | ONET FW 1.1.1 detected and needs to be updated to 1.1.4 | OPEN | Int | TBD
2025-04-04 | 180355 | 10.151.16.21 | DUC | DUC-1 | 1830PSS32-WDM | OPT_NC | 5.6.9 | FAILURE | Check ONET Amps FW | AHPHG-1-1-10-0, PN (8DG59245AAAB02), SN (EZ1324A2072) needs to be upgraded to FW 1.1.4 | ONET FW 1.1.1 detected and needs to be updated to 1.1.4 | OPEN | Int | TBD
2025-08-27 | 122967 | 10.151.20.2 | BRL | BRL-R-1 | 1830PSS32-WDM | OPT_NC | 9.7.4 | FAILURE | Check uptime of controller boards | uptime of ECA is too high: 533 days (trigger 497) | OCS: mentioned controller board needs to reset via ZIC in the next days -> 'init board'. WDM: cold reset main shelf ECs, standby EC should be checked for full redundancy prior to cold resetting the active EC. Subtending shelves are not affected. See also linked MOP. | OPEN | Int | TBD